## Mobile View
Bug ID | Status | ClickUp Status | Assigned To | Description | Expected Result | Actual Result | Assigned Date
B001 | Closed | Closed | Humza | place order -> order status screen -> remove extra space between icon and status | icon and status should be aligned in center | unnecessary space | 2024-10-11
B002 | Closed | Closed | Humza | place order of takeaway -> order status screen -> food ready -> remove rider name field, currently its showing undefined | no need of rider name in pickup orders | rider name is appearing | 2024-10-11
B003 | Closed | Closed | Humza | cart becomes empty when selecting the online payment method | onliine order should take place | stucked on place order screen with cart empyt prompt | 2024-10-11
B004 | Closed | Closed | Humza | place order of delivery/takeaway -> order status screen -> order delivered -> showing unpaid in payment status field even after payment is done | payment can't be unpaid in delivered orders | showing unpaid in payment field when order status is delivered | 2024-10-11
B005 | Closed | Closed | Humza | place order -> order status screen -> status icon disappear when order is not delivered i.e cancelled by the rider | there should be the proper status of cancelled orders | icon is disapearing if order is cancelled | 2024-10-11
B006 | Closed | Closed | Humza | app is lagging on checkout page (this issue is noticeable when the app has been open for a while or during the first checkout attempt) | The checkout page should load smoothly without any lag, regardless of how long the app has been open or during any attempt. | The app lags noticeably on the checkout page, especially when it's been open for a while or during the first checkout. | 2024-10-11
B007 | Closed | Closed | Humza | Sign up -> show any prompt like ‘user is registered’ after otp is verified | After OTP verification, a prompt confirming the user is registered should be displayed. | No confirmation prompt is shown after OTP verification. | 2024-10-14
B010 | Closed | Closed | Humza | App is CRASHING after login | The app should remain stable after login and not crash | The app crashes immediately after login. | 2024-10-14
B009 | Closed | Closed | Humza | Add address -> choose any address -> showing wrong address on addresses screen | After selecting an address, the correct address should appear on the addresses screen. | The wrong address is displayed on the addresses screen. | 2024-10-14
B010 | Closed | Closed | Humza | Checkout page is lagging after switching to pickup | The checkout page should load seamlessly after switching to pickup without any lag. | The app lags on the checkout page after switching to pickup. | 2024-10-14
B011 | Closed | Closed | Humza | App is lagging for few seconds after login | The app should function smoothly without any delay after login | The app lags for a few seconds after logging in. | 2024-10-14
B012 | Closed | Closed | Humza | Click on any restaurant -> scroll the menu -> location on top is cutting off | The location at the top should remain visible while scrolling through the menu. | The location at the top gets cut off while scrolling. | 2024-10-14
B013 | Closed | Closed | Humza | Home ->filter by free delivery -> all restaurants are offering free delivery but only 4 are appearing in list | All restaurants offering free delivery should appear in the list after applying the filter. | All restaurants offering free delivery should appear in the list after applying the filter. | 2024-10-14
B014 | Closed | Closed | Humza | Promotion -> app is lagging on every feature of this page | The promotion page should function smoothly without lag on any feature. | The app lags on every feature of the promotion page. | 2024-10-14
B015 | Closed | Closed | Humza | Open fougito pak -> discount cards -> showing null in fixed amount coupons and showing amount in % | Fixed amount coupons should display the correct discount value, and percentage-based coupons should display the correct percentage. | Fixed amount coupons are showing "null," and percentage-based coupons are showing values incorrectly. | 2024-10-14
B016 | Closed | Closed | Humza | Open any restaurant -> click on info icon -> img is not proper on restaurant info page also there is unnecessary icon of three dots on this page | The image on the restaurant info page should display correctly, and no unnecessary icons should be present. | The image is not properly displayed, and the three dots icon appears unnecessarily on the page. | 2024-10-14
B018 | Closed | Closed | Humza | Click any restaurant -> choose address -> show out of delivery zone page if user selected the out of radius address (check figma) | As per figma, if an out-of-radius address is selected, a page indicating that the address is out of the delivery zone should appear. | The out-of-delivery zone page is not displayed after selecting an out-of-radius address. | 2024-10-14
B019 | Closed | Closed | Humza | Home -> only icons are appearing and dishes are missing in featured restaurant and all restaurant list before apply filter | Both icons and dishes should appear for featured and all restaurants | Only icons are appearing, and dishes are missing | 2024-10-14
B020 | Closed | Closed | Humza | Promotion -> selected cuisine should appear with filter as per figma | After applying the cuisine filter, the selected cuisine should appear as a filter option, matching the Figma design. | The selected cuisine is not appearing with the filter | 2024-10-14
B021 | Closed | Closed | Humza | Food issue/ delivery issue -> feedback not submitting | The feedback should be successfully submitted | Feedback is not being submitted. | 2024-10-14
B022 | Closed | Closed | Humza | Support screen -> call now -> wrong number appearing on dial screen | The correct support number should appear on the dial screen when clicking 'Call now.' | An incorrect number is displayed on the dial screen. | 2024-10-14
B023 | Closed | Closed | Humza | Click on any item -> add to cart button is hiding when adding special instruction | The add to cart button should remain visible and functional when a special instruction is being added. | he add to cart button hides when adding a special instruction | 2024-10-15
B024 | Closed | Closed | Humza | Cart -> increase and decrease quantity buttons not working smoothly | The increase and decrease quantity buttons should work smoothly without any lag | The buttons are not working smoothly, causing delays | 2024-10-15
B025 | Closed | Closed | Humza | Cart -> popular with your order items not adding | Items listed under 'Popular with your order' should be easily added to the cart. | The items from 'Popular with your order' are not being added to the cart. | 2024-10-15
B026 | Closed | Closed | Humza | 5. Cart -> click on add instruction -> prices are overflowing if item name is long | Prices should be properly aligned and not overflow, even when the item name is long. | Prices are overflowing and misaligned when the item name is too long. | 2024-10-15
B027 | Closed | Closed | Humza | 6. Cart -> click on add instruction -> close button not working smoothly | The close button should work smoothly without any lag | The close button is not functioning smoothly | 2024-10-15
B028 | Closed | Closed | Humza | 7. Continue with phone number -> click on country code -> click on search field -> unnecessary splash | No unnecessary splash screen should appear when interacting with the country code | An unnecessary splash appears when clicking on country code. | 2024-10-15
B029 | Closed | Closed | Humza | 8. Continue with phone number -> replace choose password placeholder with new password | The placeholder text should be 'new password' | The placeholder still says 'choose password' instead of 'new password.' | 2024-10-15
B030 | Closed | Closed | Humza | 9. open the app -> delivery address screen should appear on whole page | The delivery address screen should occupy the entire page upon app launch | The delivery address screen is not taking up the full page as expected. | 2024-10-15
B031 | Closed | Closed | Humza | 10. open the app -> delivery address page -> change the location by dragging the pointer -> then click on locate me -> not moving to live location | When the user clicks on 'locate me,' the map should move to the current live location. | Clicking on 'locate me' does not move the map to the live location after manually dragging the pointer. | 2024-10-15
B032 | Closed | Closed | Humza | 11. place order -> order status screen -> items text is overflowing when item name is long | Item names should be displayed properly to prevent text overflow on the order status screen. | Item names are overflowing and not displayed correctly when they are long. | 2024-10-15
B033 | Closed | Closed | Humza | 12. app is lagging on delivery address module on both home and checkout pages | The delivery address module should load and function smoothly on both the home and checkout pages. | The app is lagging when interacting with the delivery address module on both pages. | 2024-10-15
B034 | Closed | Closed | Humza | 13. calculation section should be synced on cart and checkout screen | The calculation of totals (including taxes, discounts, etc.) should be synchronized and consistent between the cart and checkout screens. | The calculations are not properly synced between the cart and checkout screens. | 2024-10-15
B035 | Closed | Closed | Humza | Coupon code -> apply -> lagging | Applying a coupon code should be fast and without delay. | The app lags after applying a coupon code. | 2024-10-15
B036 | Closed | Closed | Humza | 16. Click on any restaurant -> click on coupon discount -> UI issue on discount card | The coupon discount card should display properly without any UI issues | The discount card displays incorrectly with UI issues. | 2024-10-15
B038 | Closed | Closed | Humza | Home -> choose category -> view the list of restaurants with that category -> open any one restaurant -> selected category is not there | Correct restaurant should filter down actually having that category | Restaurants not having that category is also filtering down | 2024-10-15
B039 | Closed | Closed | Humza | Home -> App lagging on view all button | The 'View all' button should function smoothly without causing any lag | The app lags when the 'View all' button is clicked. | 2024-10-16
B040 | Closed | Closed | Humza | Place order -> on home status bar appearing of order status ->showing rider has picked up your order’ on pending status | The order detail should accurately reflect the current status | Showing "Rider has picked up your order" even when the order is still pending. | 2024-10-17
B041 | Closed | Closed | Humza | Showing 15% discount on pickup but in calculation no discount has given | A 15% discount should be applied to the final total when selecting pickup | Although the 15% discount is displayed, no discount is actually applied in the calculation. | 2024-10-17
B042 | Closed | Closed | Humza | Checkout page -> remove delivery fee field from pickup orders | The delivery fee field should not appear when a pickup order is selected | The delivery fee field is still visible, even for pickup orders. | 2024-10-17
B043 | Closed | Closed | Humza | Home -> app lagging on view category button also when choosing categories from view all and closing view all modal | Both the 'View category' button and the 'View all' modal should function without lag or delays. | The app lags when using the 'View category' button and while interacting with the 'View all' modal. | 2024-10-17
B044 | Closed | Closed | Humza | Order status on home screen become unresponsive or hanging when placing multiple order and updating their statuses | The order status should update smoothly and remain responsive, even when placing multiple orders. | The order status becomes unresponsive or hangs when managing multiple orders | 2024-10-17
B045 | Closed | Closed | Humza | Placed order of fougito order -> but when order is delivered it is asking the rating for tikka paaji | The rating prompt should appear for the correct restaurant and order | The app asks for a rating for a different restaurant (Tikka Paaji) instead of the correct one. | 2024-10-17
B046 | Closed | Closed | Humza | Order cancelled -> status bar on home screen is showing arriving time and rider has picked up your order even on cancelled\not delivered orders | Once an order is canceled, the status bar should not display information related to order delivery or arrival time. | Even after order cancellation, the status bar still shows "Rider has picked up your order" and an estimated arrival time. | 2024-10-17
B047 | On Hold | On Hold | Humza | Place order -> pending status bar is appearing after few seconds on home screen | he pending status should appear immediately upon placing an order. | The pending status bar takes a few seconds to appear on the home screen after placing an order. | 2024-10-17
B048 | Closed | Closed | Humza | After submitting review -> thankyou prompt is appearing again n again | The 'Thank you' prompt should appear only once after submitting a review. | The 'Thank you' prompt keeps reappearing multiple times after submitting the review. | 2024-10-17
B049 | Closed | Closed | Humza | Place pick up order -> showing arriving time and rider picked your order even on picked up orders | On pickup orders, there should be no information about delivery, such as arriving time or rider status. | The app is still showing arriving time and "Rider picked up your order" for pickup orders | 2024-10-17
B050 | Closed | Closed | Humza | Asking for rating only on first order after login | The app should ask for a rating after each completed order, not just the first one. | The rating prompt only appears after the first order and doesn’t show for subsequent orders. | 2024-10-17
B051 | Closed | Closed | Humza | App lagging on checkout page | The checkout page should load and function without any lag or delays | The app lags on the checkout page, making the user experience slow | 2024-10-17
B053 | Closed | Closed | Humza | Showing rating prompt every time when opening the app | The rating prompt should only appear once after an order is delivered or after a certain action, not every time the app is opened. | The rating prompt appears every time the app is launched. | 2024-10-17
B054 | Closed | Closed | Humza | Open any restaurant -> add products in cart -> go to promotion -> same view cart button is appearing in promotion too with same calculation | The promotion screen should not display the 'View cart' button or reflect the cart’s calculation from the previous screen. | The 'View cart' button and its calculations appear on the promotion screen, causing confusion. | 2024-10-17
B055 | Closed | Closed | Humza | Promotion discount is not applying | The discount from the promotion should be applied to the order during checkout. | The promotion discount is not being applied during checkout, even though it is displayed. | 2024-10-17
B056 | On Hold | On Hold | Humza | Not receiving otp on email | The OTP should be sent to the user's registered email when requested for verification. | The user is not receiving the OTP on their email | 2024-10-18
B057 | On Hold | On Hold | Humza | Review not appearing on portal | Reviews submitted by the user should appear on the restaurant’s page or portal. | Reviews are not being reflected on the portal even after submission. | 2024-10-18
B058 | Closed | Closed | Humza | User not logged in -> user select items and proceeds to place an order -> app redirects to login sign up page -> user successfully logged in -> after login user is redirected to homepage -> delivery location on top is changing automatically again and again causing lag in app | After logging in, the user should be redirected back to the order flow, and the delivery location should remain stable. | After login, the user is redirected to the homepage, and the delivery location changes repeatedly, causing the app to lag. | 2024-10-18
B059 | Closed | Closed | Humza | New order status is replacing previous order status on home screen | The home screen should show the status of all active orders without replacing previous order statuses. | The new order status is replacing the previous one, making it difficult to track multiple orders. | 2024-10-18
B060 | Closed | Closed | Humza | Account info -> ui issue DOB field | The DOB field should display correctly | There’s a UI issue with the DOB field | 2024-10-18
B061 | Closed | Closed | Humza | Showing splash of undefined with location prompt when opening app | The location prompt should display clearly without any 'undefined' messages. | n 'undefined' splash screen appears alongside the location prompt | 2024-10-18
B062 | Closed | Closed | Humza | Changed delivery address from menu but on checkout page that address is not reflecting | Once the delivery address is changed in the menu, it should be updated and reflected on the checkout page. | The new delivery address is not showing up on the checkout page, causing confusion for the user. | 2024-10-18
B063 | Closed | Closed | Humza | Place order -> showing wrong delivery address on order status screen uploaded | The correct delivery address should appear on the order status screen after placing an order. | The wrong delivery address is displayed on the order status screen | 2024-10-18
B064 | Closed | Closed | Humza | Addresses -> edit address -> map missing | The map should be visible when editing an address, allowing users to pinpoint their exact location. | The map is missing when trying to edit an address | 2024-10-21
B065 | On Hold | On Hold | Humza | Statuses are updating after few second but not immediately | Order statuses should update immediately after a change in status. | There is a delay of a few seconds before the status is updated on the app | 2024-10-21
B066 | Closed | Closed | Humza | Order status is hanging when placing multiple orders and updating their statuses | The order status screen should remain responsive and update smoothly when handling multiple orders. | The order status becomes unresponsive or hangs when managing multiple orders and their status updates. | 2024-10-21
B067 | Closed | Closed | Humza | App lagging on delivering to whole module | The delivery module should load and function smoothly without lag, enabling users to quickly select delivery options. | The app lags while interacting with the delivery module, causing a slowdown in the user experience. | 2024-10-21
B068 | Closed | Closed | Humza | Select category -> app lagging on selecting and deselecting filters | Selecting and deselecting filters should be quick and responsive without any delay. | The app lags when users select or deselect filters, slowing down navigation and filtering. | 2024-10-21
B069 | Closed | Closed | Humza | Select category -> app lagging on view list icons | The view list icons should load and function without any lag | The app experiences lag when users view the list icons | 2024-10-21
B070 | Closed | Closed | Humza | Select category -> restaurant search filters not working properly (when I'm searching fougito its workig propeprly but when I'm searching babylon it is showing no results found) | The restaurant filters should work correctly and display relevant results | The restaurant filters are not functioning properly, either showing incorrect results or failing to apply | 2024-10-21
B071 | Closed | Closed | Humza | Home -> view all -> search any category -> select -> on restaurant’s page -> click on cuisines -> close cuisines -> category filter removed | The category filter should remain applied | The category filter is removed, leading to inconsistent filtering behavior. | 2024-10-21
B072 | Closed | Closed | Humza | Addresses -> click on any address -> replace ‘---’ with valid building/area name | The address should display a valid building or area name instead of dashes '---'. | The address is showing '---' in place of a proper building or area name | 2024-10-21
B073 | Closed | Closed | Humza | Place order -> order status screen -> showing review status again and again on this screen | The review prompt should appear once after the order is delivered, and should not reappear multiple times on the order status screen. | The review status keeps appearing repeatedly on the order status screen, even after submission. | 2024-10-21
B074 | Closed | Closed | Humza | addresses -> click on any address -> edit address -> on edit page, selected ordered should reflect instead of live location | When editing an address, the selected order address should be pre-filled and reflected on the edit page so that users can modify the specific address they selected during the order process. | The live location is being shown instead of the selected order add | 2024-10-21
B075 | Closed | Closed | Humza | Account info -> remove extra space between first and last name | There should be no extra space between the first and last name fields | Extra space is appearing between the first and last name | 2024-10-22
B076 | Closed | Closed | Humza | Click on any restaurant -> reviews -> add review -> rating stars should be center aligned | The rating stars on the 'Add review' screen should be center-aligned | The rating stars are not center-aligned | 2024-10-22
B077 | Closed | Closed | Humza | if user is adding long special insruction then in cart, item is hiding from top also instruction is cutting from bottom | When a long special instruction is added, both the item and the instruction should be fully visible in the cart | The item is being hidden from the top, and the special instruction is being cut off from the bottom, making it difficult for users to review the entire item and instruction on cart screen | 2024-10-22
B078 | Closed | Closed | Humza | restaurant info -> clicking on map should navigate to google maps | Clicking on the map within the restaurant info section should open the location in Google Maps for navigation. | Clicking on the map does not navigate to Google Maps | 2024-10-22
B079 | Closed | Closed | Humza | Featured Restaurant: On clicking fougito restaurant tile, showing babylon bites on menu. | Clicking on the FouGito restaurant tile should display all branches | After clicking on the FouGito restaurant tile, the Babylon Bites menu is shown | 2024-10-22
B080 | Closed | Closed | Humza | home -> click on deliver to -> in choose delivery location modal, deliver to different location is cutting from bottom when multiple addresses are saved | The 'Deliver to different location' text should be fully visible, regardless of the number of saved addresses. | The 'Deliver to different location' text is being cut off from the bottom | 2024-10-22
B081 | Closed | Closed | Humza | add a refresh feature on home page | A refresh feature should be added to the home page, allowing users to manually refresh the content | Currently, there is no refresh feature on the home page | 2024-10-22
B082 | Closed | Closed | Humza | home -> order status -> after time is finished status has turned into undefined | Once the timer for an order status is finished, the status should update to reflect the correct next step | After the time finishes, the order status turns into 'undefined' | 2024-10-22
B083 | Closed | Closed | Humza | home -> search -> search any item -> in suggestions, that item is appearing two times | Each item should appear only once in the search suggestions list | The same item is displayed twice in the search suggestions | 2024-10-23
B084 | Closed | Closed | Humza | The app crashes randomly after being opened | The app should launch successfully | The app crashes intermittently after being opened, causing it to close unexpectedly | 2024-10-23
B085 | Closed | Closed | Humza | App crashes or changes address on home screen after selecting "Start Ordering" | The app should allow the user to proceed with their order smoothly, keeping the address on the home screen unchanged and avoiding crashes | In some cases, the app crashes after clicking "Start Ordering." In other cases, the app does not crash, but the address on the home screen changes unexpectedly without user input. | 2024-10-23
B086 | Closed | Closed | Humza | if user is searching item from popular or recent seraches, the searched item is not displaying in search field | The selected item should appear in the search field | The search field remains empty, even though an item was selected from the popular or recent searches list. | 2024-10-23
B087 | Closed | Closed | Humza | App lagging on multiple pages, especially when opening restaurant, menu, and promotion pages | The app should load all pages smoothly without any lag or delay. | The app lags is lagging on: Opening a restaurant after selecting a category. Navigating to the menu or promotion pages. | 2024-10-23
B088 | Closed | Closed | Humza | When a user tries to add a review under the restaurant info section, an alert is displayed, and the review is not uploaded | The review should be uploaded successfully, and the user should receive confirmation that their review has been posted. | An alert message is shown when trying to submit the review, and the review is not uploaded to the restaurant page | 2024-10-23
B089 | Closed | Closed | Humza | home -> change restaurant -> taking time in browsing resturants as per the location | The list of restaurants should load quickly after selecting a location. | There is a noticeable delay in browsing restaurants based on the selected location. | 2024-10-23
B091 | Closed | Closed | Humza | checkout -> clicking on map should navigate to google maps | Clicking on the map should open Google Maps to display the selected location | Clicking on the map does not navigate to Google Maps as expected. | 2024-10-23
B092 | Closed | Closed | Humza | login with google -> if user have multiple accounts and he logged in from one -> user logged out from that account and wanted to login with different google account but itis not showing prompt of all accounts even after removing the app from background | Upon login, a prompt should appear to allow the user to choose among multiple Google accounts | No prompt is shown for account selection, even after removing the app from the background | 2024-10-28
B093 | Closed | Closed | Humza | app is crashing randomly when user is logging in or logging out | The app should handle login and logout smoothly without crashing | The app should handle login and logout smoothly without crashing | 2024-10-28
B094 | Closed | Closed | Humza | add address -> save address -> click on add address again -> address previously added is reflecting while adding address | A blank form should be displayed for adding a new address | The previously saved address details are visible in the fields | 2024-10-28
B095 | Closed | Closed | Humza | address -> click on any saved address -> edit -> location of aved address should appear on map instead of live location | The map should show the location of the saved address | The map displays the live location instead of the saved address location | 2024-10-28
B096 | Closed | Closed | Humza | login with google -> choose delivery location modal is cutting from bottom. this issue is only appearing on google accounts | The entire delivery location modal should be fully visible | The modal is cut off at the bottom, only for Google login users | 2024-10-28
B098 | Closed | Closed | Humza | featured restaurants -> select cuisine -> app lagging while opening and closing modal | The modal should open and close smoothly. | The app lags significantly while opening and closing the cuisine modal. | 2024-10-28
B099 | Closed | Closed | Humza | featured restaurants -> app lagging when user clicking on any filter | Filters should apply without delay | The app lags when clicking on filters | 2024-10-28
B100 | Closed | Closed | Humza | login with google -> showing error when user is placing order | The order should process without issues | An error appears when placing an order | 2024-10-28
B101 | Closed | Closed | Humza | added items in one account -> logged out and logged in google account -> the cart of previous account is visible in new logged in account | The cart should be empty in the new account | The cart items from the previous account are visible in the new account | 2024-10-28
B102 | Closed | Closed | Humza | home -> choose any saved address -> click on any promotion -> not opening (only showing loader) | The selected promotion should open without issues | Only a loading indicator appears, and the promotion does not open | 2024-10-28
B103 | On Hold | On Hold | Humza | suggestion -> there should be the icon of cart in the app from where user can checkout, currently user can only see cart when he is in the menu of the restaurant | A cart icon should be consistently visible across the app, allowing users to view and proceed to checkout at any time | The user can only view and access the cart within the restaurant menu | 2024-10-28
B104 | Closed | Closed | Humza | home -> top eats nearby -> fougito restaurant is not offering free delivery but free delivery is written below the restaurant name | Only restaurants that are offering free delivery should display "Free Delivery" below their name | Fougito Restaurant has "Free Delivery" displayed below its name, even though it does not offer free delivery. | 2024-10-29
B105 | Closed | Closed | Sameed | added a description in promotion but its missing in app | description should appear in promo card to see the details | description is missing | 2024-10-25
B106 | Closed | Closed | Sameed | home -> click on delivering to -> delivery location modal is opening with splash | The Delivery Location Modal should open smoothly without any splash screen | The Delivery Location Modal opens with a splash screen effect | 2024-10-29
B107 | Closed | Closed | Sameed | home ->delivery location -> view all -> from view all list select any address -> that address should visible in delivery location field but currently its navigating to edit page | After selecting an address from the "View All" list, the selected address should appear in the delivery location field. | The app navigates to the edit page instead of updating the delivery location field with the selected address. | 2024-10-31
B108 | Closed | Closed | Sameed | restaurant info -> free delivery spelling is wrong | The correct spelling should display as "Free Delivery" in the restaurant info section | "Free Delivery" is misspelled in the restaurant info section. | 2024-10-31
B109 | Closed | Closed | Sameed | restaurant info > tagline should appear below restaurant name | The tagline in the restaurant information page is not displayed | The tagline should appear below the restaurant name | 2024-10-31
B110 | Closed | Closed | Humza | home: cuisines are missing on restaurant tile, featured restaurant page and restaurant page: only icon appearing and cuisine is missing | Cuisine names should be displayed alongside the icon on restaurant tiles | Only the cuisine icon is visible; cuisine names are missing. | 2024-11-01
B111 | Closed | Closed | Humza | restaurants/featured restaurants -> filter should get remove when user navigate to home again | Filters should reset upon navigating back to the home page and should not persist when returning to the Restaurants or Featured Restaurants page. | Filters should reset upon navigating back to the home page and should not persist when returning to the Restaurants or Featured Restaurants page. | 2024-11-01
B112 | Closed | Closed | Humza | coupon should get removed when the order is placed currently its automatically applying on next order too | Coupons should be cleared after an order is placed and should not automatically apply to the next order. | The previously applied coupon is automatically applied to the next order. | 2024-11-01
B113 | Closed | Closed | Humza | User not logged in -> user select items and proceeds to place an order -> app redirects to login sign up page -> user successfully logged in -> after login user is redirected to homepage (this iissue is only appearing in google accounts) | After logging in, the user should be redirected back to the order flow, and the delivery location should remain stable. | After login, the user is redirected to the homepage, and the delivery location changes repeatedly, causing the app to lag. | 2024-10-18
B114 | Closed | Closed | Humza | checkout page -> edit address -> place order -> see in calculation that discount has removed | The discount should remain applied after editing the address. | The discount is removed from the total calculation after editing the address, leading to an incorrect order amount. | 2024-11-01
B115 | Closed | Closed | Humza | When applying a coupon of 25% on a total amount of 70, the expected discount should be 17.50. However, the coupon discount is calculated as 12.50, which is incorrect | The discount amount should be correctly calculated | The discount amount is incorrectly displayed | 2024-11-01
B116 | Closed | Closed | Humza | on facebook and google account -> do not give the option to update profile picture on account info page | Google or facebook profile picture should appear | Giving the option to update img but img is not updating | 2024-11-01
B117 | Closed | Closed | Humza | Sometimes need to click multiple times on these buttons: 1. Search icon on the home page 2. Profile icon on the home page 3. Settings icon on the account info page 4. Search icon on the delivery address page 5. Restaurant info button on the menu 6. Choose category icon on the menu 7. Add instruction button on the cart 8. Favourites button on the menu 9. Search button on the restaurants page 10. Back button on the menu 11. Back button on the restaurants page |  |  | 2024-11-04
B118 | On Hold | On Hold | Sameed | Here are the points where the API is taking response time: 1. Opening the restaurant's menu 2. Opening restaurants after selecting a category 3. Proceeding to the checkout screen 4. Opening the order status screen after placing an order 5. Opening the orders page 6. Opening any order from the orders page 7. Opening the home page after clicking the 'Browse Restaurants' button on the favorites page 8. Opening the promotions page 9. Opening cuisines after clicking 'View All' from the home page 10. Applying a filter on restaurants 11. Opening the home page after clicking the 'Start Ordering' button on the promotions page 12. Opening the home page after login 13. Updating the order status |  |  | 2024-11-04
B119 | Closed | Closed | Humza | home -> user select category -> click on back -> category should get removed when user again navigting to home page currently the selsected category is appearing on home page filters | The previously selected category should be removed | The selected category still appears on the home page filters. | 2024-11-05
B120 | Closed | Closed | Humza | on account info screen, flag is not updating after selecting different country from dropdown | The flag should update to match the selected country | The flag should update to match the selected country | 2024-11-06
B121 | Closed | Closed | Humza | on chechkout screen, flag is not updating after selecting different country from dropdown | The flag should change to reflect the newly selected country | The flag does not update to reflect the change. | 2024-11-06
B123 | Closed | Closed | Humza | login with google -> google account number should correctly appear on account info and checkout screen currently its showing wrong country code | The correct country code should appear with the Google account number | The displayed country code is incorrect. | 2024-11-06
B124 | Closed | Closed | Humza | login -> click on contact us -> showing login successfully prompt on first time | The "Contact Us" page should open without a login success prompt. | A "Login Successfully" prompt appears the first time "Contact Us" is clicked. | 2024-11-06
B126 | Closed | Closed | Sameed | google login -> no need of verification code every time when user is logging in | A verification code should not be requested each time the user logs in with Google | A verification code is requested every time the user logs in with Google. | 2024-11-06
B127 | Closed | Closed | Humza | login in with google -> add phone number on checkout screen -> showing null instead of country code on verify number screen | The correct country code should appear on the Verify Number screen | "Null" appears instead of the correct country code | 2024-11-06
B129 | Closed | Closed | Humza | Incorrect Icon Displayed on Account Deletion Success Prompt | The success prompt should display a "✓" (tick) icon, indicating successful deletion | The success prompt displays a "!" (exclamation) icon, suggesting a warning or issue instead of a successful deletion. | 2024-11-08
B130 | Closed | Closed | Humza | login with new google account -> account info - > showing null with verified icon on phone number field | The phone number field should be blank if no number is provided. |  | 2024-11-08
B132 | Closed | Closed | Humza | wrong text on delete account screen | The text should clearly and accurately convey the account deletion process | The displayed text is incorrect or misleading | 2024-11-08
B133 | Closed | Closed | Humza | delete account screen -> select the long reason -> UI issue (reason is not properly visible in the field) | The entire selected reason text should be visible within the field | The selected reason is partially cut off | 2024-11-08
B134 | Closed | Closed | Humza | Remove country code dropdown option and set default to UAE | The country code dropdown should be removed entirely, preventing users from selecting other country codes. | Users can select other country codes, and UAE is not set as the default. | 2024-11-11
B135 | Closed | Closed | Humza | login with email -> delete account -> add wrong password in delete account screen -> showing the prompt of account deleted successfully | Even after entering the wrong password, the system displays a prompt saying "Account deleted successfully" | When the wrong password is entered, an error prompt should appear, indicating the incorrect password | 2024-11-11
B136 | Closed | Closed | Humza | user is logged out -> place order -> place order button is disable and prompt is appearing of no user exist | After the user is logged out, the "Place Order" button remains disabled, and a prompt of "No user exists" appears. | The "Place Order" button should be activate and navigate to login screen | 2024-11-11
B137 | Closed | Closed | Humza | Cart -> Apply coupon code -> Navigate back -> Navigate to cart again -> Coupon code removed | When navigating away from the cart after applying the coupon code, the coupon code gets removed upon returning to the cart. | The coupon code should remain applied even when navigating away from and back to the cart. | 2024-11-11
B138 | Closed | Closed | Humza | Menu -> Add items from popular with your order -> Amount is adding, but selected item is missing from the items list | The total amount increases as expected, but the selected item doesn't appear in the items list. | The selected item should appear in the items list along with the updated total amount. | 2024-11-11
B139 | Open | Open | Sameed | Promotion -> Number of total redemptions is not working properly -> Total is 2 but coupon is applying to more than 2 orders | The coupon is being applied to more than the set number of redemptions (more than 2 orders). | The coupon should only apply to the correct number of redemptions, i.e., 2 orders, and should not be applicable after that. | 2024-11-11
B140 | Closed | Closed | Sameed | images are missing on popular with your order | Images for items listed under "Popular with Your Order" are not displayed | Each item under "Popular with Your Order" should display its respective image | 2024-11-12
B141 | Closed | Closed | Humza | checkout -> order summary -> showing 0 price of items having multiple options to select | Items with variations options display a price of 0 in the order summary. | The correct total price for each item, based on selected options, should appear in the order summary. | 2024-11-12
B142 | Closed | Closed | Humza | create account -> offers and discount field should be uncheck by default | The "Offers and Discounts" checkbox should be unchecked by default, allowing users to opt-in if desired. | The "Offers and Discounts" checkbox is selected by default during account creation. | 2024-11-12
B143 | Closed | Closed | Humza | if user has selected address before login then do not ask for address again after logged out | If the user selected an address before logging in, the app should remember this address and not prompt the user to select it again after logging out. | After logging out, the user is prompted to select an address again, even if they had previously selected one | 2024-11-12
B144 | Closed | Closed | Humza | if user is opening app with dubai location, he should be seen his live location currently Karachi's live location is locked | Upon opening the app with Dubai as the location, the app should detect and display the user's actual live location. | When opening the app with the Dubai location selected, the user's live location does not update and defaults to Karachi. | 2024-11-12
B145 | Closed | Closed | Humza | when user is login, unable to place order, button is disabled. | The "Place Order" button should be enabled after the user logs in, allowing them to place an order. | After logging in, the "Place Order" button remains disabled, preventing order placement. | 2024-11-12
B146 | Closed | Closed | Humza | account info -> click on verify button without entering number -> make the k of kindly capital | The message should start with a capital "K" | In the prompt message, "kindly" is lowercase | 2024-11-12
B147 | Closed | Closed | Humza | checkout screen -> change address to current location -> location is upating but map is not updating | Both the address and map should update to reflect the location selected by the user. | When the user Change Address the location updates, but the map remains the same. | 2024-11-12
B148 | Closed | Closed | Sameed | menu -> switch to pickup -> distance should be accurate currently its showing same distance for all locations | The distance should dynamically update to show the correct distance between the user’s location and each available pickup location. | Switching to Pickup shows the same distance for every location, regardless of actual proximity. | 2024-11-12
B149 | Closed | Closed | Sameed | first coupon created on portal should apppear on restaurant card as off | The first coupon created on the portal should correctly appear on the restaurant card | The first coupon created on the portal does not display on the restaurant | 2024-11-12
B150 | Closed | Closed | Humza | menu -> switch to delivery -> replace delivery time with average delivery time | Replace delivery time with average delivery time | its showing only delivery time | 2024-11-12
B151 | Closed | Closed | Humza | meni -> only few cuisines should be visible initially, with the rest hidden behind a "More" (dots) icon and clicking on the "More" icon should reveal more cuisines. | Only a limited number of cuisines should be visible by default | All cuisines are displayed initially | 2024-11-12
B152 | Closed | Closed | Humza | checkout -> order summary -> the total amount shown in the order summary only reflects the price of a single item, | The order summary should show the total amount for all items, including their quantities | The total amount in the order summary only reflects the price of one item | 2024-11-12
B153 | Closed | Closed | Humza | order cancelled by rider -> status icon removed from order status page also on home page status is not updating if order has cancelled. | When an order is canceled by the rider, the status icon is removed from the Order Status page. The order status on the Home page does not update to reflect that the order has been canceled | If an order is canceled by the rider, a status icon indicating "Canceled" should remain visible on the Order Status page. The Home page should also update to show the order as "Canceled" to keep the user informed of the current order status. | 2024-11-13
B154 | Closed | Closed | Humza | order cancelled from pos/portal -> on home page status is not updating. | When an order is canceled via the POS or portal, the Home page does not show an updated status reflecting the cancellation. | When an order is canceled from the POS or portal, the Home page should update to display the order as "Canceled," | 2024-11-13
B156 | Closed | Closed | Humza | On performing a series of actions in the cart, including adding items, increasing quantities, removing items, and re-adding items, the total calculation shows a negative amount. | The cart should reflect a correct positive total based on the items and quantities added. | The cart shows a negative total after the above steps, resulting in incorrect calculations. | 2024-11-14
B157 | Closed | Closed | Humza | order status screen -> Estimated deliveery time should get removed when the order is delivered | Estimated delivery time still shows on the order status screen even after the order is marked as delivered. | Once the order is delivered, the estimated delivery time should no longer be displayed on the order status screen. | 2024-11-14
B158 | Closed | Closed | Humza | showing shahrah e faisal location on map if user's location is off | The map defaults to Shahrah-e-Faisal when the user’s location is disabled | If the user's location is off, the app should display a message like "Location not available" | 2024-11-15
B160 | Closed | Closed | Humza | cart -> special instructions -> prices are hiding if item has a long name | The price of an item in the cart is hidden when the item's name is too long | The cart layout should dynamically adjust to ensure that the price is always visible | 2024-11-15
B161 | Closed | Closed | Humza | app is crashing sometimes after logout | The app crashes intermittently when the user logs out | The app should not crash after logout | 2024-11-15
B162 | Closed | Closed | Humza | open menu -> searh item -> app is crashing on search | The app crashes when the user attempts to search for an item in the menu. | The app should allow the user to search for items in the menu seamlessly | 2024-11-18
B163 | Closed | Closed | Humza | favorites -> no favorites -> text issue. it should be 'start adding your favourites restaurats to see them easily' | The text displayed when there are no favorites is incorrect | The text should be corrected | 2024-11-18
B164 | Closed | Closed | Humza | menu -> search item -> item is appearig two times
B165 | Closed | Closed | Humza | rating pop is appearing multiple times after submitting the rating
B166 | Closed | Closed | Humza | rating pop up -> type something in the text field -> text is hiding under the keyboard
B167 | Closed | Closed | Humza | menu search -> show text 'Sorry, no item found with this name' if user seaarch an item which is not present in the list
B168 | Closed | Closed | Sameed | order delivered -> showing cash on order status screen on all delivery methods
B169 | Open | Open | Sameed | calculation issue in discount precentage promotion (discount amount is changed on order status screen)
B171 | Closed | Closed | Humza | rating pop up appearing again and again after closing it without submitting the feedback
B172 | Closed | Closed | Humza | reel ordering -> added video and thumbnail from portal -> app crashing when playing that video on app |  |  | 2024-11-26
B173 | Closed | Closed | Humza | reel ordering -> no option to see the full description of an item |  |  | 2024-11-26
B174 | Closed | Closed | Humza | reel ordering -> location and category (header) text is not clearly readable |  |  | 2024-11-26
B175 | Closed | Closed | Humza | the first video in the reel ordering section displays correctly on the screen. However, upon scrolling, an unnecessary margin appears below videos and their text (only 1 video should appear at a time) |  |  | 2024-11-26
B176 | Closed | Closed | Sameed | reel ordering -> thumbnail should not appear more than 1 sec currently its taking few second before playing the video |  |  | 2024-11-26
B177 | Closed | Closed | Sameed | reel ordering -> thumbnails appear correctly during the initial scroll. However, after multiple scrolling (from top to bottom and bottom to top), the thumbnails stop appearing, and a white screen is displayed instead. |  |  | 2024-11-26
B179 | Closed | Closed | Sameed | order status screen -> order is delivered, showing cash on partial and aggregator payment |  |  | 2024-11-28
suggestion: there should be a pause button on the video
B180 | Closed | Closed | Humza | restaurant min order is not working correctly with coupon, if amount become less after applying coupon then it is allowing user to order less than min order amount |  |  | 2024-11-29
B181 | Closed | Closed | Humza | time is appearing wrong on status bar on home page although its appearing corrct on order status screen (demo) |  |  | 2024-11-29
app is crashing sometimes on login

## Tablet View
Bug ID | Status | ClickUp Status | Assigned To | Description | Expected Result | Actual Result
B001 | Closed | Closed | Humza | home -> deliver to current location option is missing | The 'Deliver to current location' option should be clearly visible | The 'Deliver to current location' option is missing | 2024-10-22
B002 | Closed | Closed | Humza | home -> click on deliver to -> in choose delivery location modal, deliver to different location is cutting from bottom when multiple addresses are saved | The 'Deliver to different location' text should be fully visible, regardless of the number of saved addresses. | The 'Deliver to different location' text is being cut off from the bottom | 2024-10-22
B003 | Closed | Closed | Humza | home -> click on search -> recent and popular earches text is cutting from bottom | The 'Recent' and 'Popular searches' text should be fully visible | The text for 'Recent' and 'Popular searches' is getting cut off at the bottom | 2024-10-22
B004 | Closed | Closed | Humza | home -> promotion cards -> text is hiding from bottom | The text on the promotion cards should be fully visible | The text at the bottom of the promotion cards is being hidden | 2024-10-22
B005 | Closed | Closed | Humza | click on any restaurant -> restaurant info -> drag map manually -> menu from previous screen is reflecting on map | When viewing the restaurant info and dragging the map, only the map and related UI should be visible, without elements from the previous screen | The menu from the previous screen is reflecting or overlapping on the map when dragged.. | 2024-10-22
B006 | Closed | Closed | Humza | order status screen -> give top margin to order no on top | The order number on the order status screen should have a sufficient top margin, making it properly aligned and easily readable | The order number lacks adequate top margin, causing it to appear too close to the top edge | 2024-10-22
B008 | Closed | Closed | Humza | Give top margin to cart and checkout headings on top | The cart and checkout headings should have proper top margin | The cart and checkout headings are positioned too close to the top edge | 2024-10-22
B009 | Closed | Closed | Humza | Cart -> minus icon UI issue | The minus (decrease quantity) icon should be clearly visible | The minus icon is not clearly visible | 2024-10-22
B010 | Closed | Closed | Humza | click on any restaurant -> click on coupon card -> text is hiding from bottom and last line is completely missing | The entire text on the coupon card should be fully visible, with no lines cut off or hidden | The text at the bottom of the coupon card is being hidden, and the last line of the text is completely missing, making it difficult for users to view the full coupon details | 2024-10-22
B011 | Closed | Closed | Humza | home page is not opening on complete page and unnecesarry white border is appearing on bottom | The home page should open in full screen without any unnecessary borders | The home page is not opening on the full page, and an unnecessary white border is appearing at the bottom | 2024-10-22
B012 | Closed | Closed | Humza | Click on any item -> add to cart button is hiding when adding special instruction | The add to cart button should remain visible and functional when a special instruction is being added. | he add to cart button hides when adding a special instruction | 2024-10-25
B013 | Closed | Closed | Humza | home -> scroll till top eats nearby section, top eats nearby showing 2 times. | Top eats nearby will only show on the nearby restaurant section. | Top eats nearby showing 2 times. | 2024-10-25
B014 | Closed | Closed | Humza | verification screen -> close button is cutting off from bottom | The close button should be fully visible and accessible on the screen. | The close button is cut off at the bottom, making it partially inaccessible. | 2024-11-06
B015 | Closed | Closed | Humza | account setting screen -> phone number field border is not proper | The phone number field should have a complete and consistent border | The border of the phone number field appears improper ( | 2024-11-08
B016 | Closed | Closed | Humza | reel ordering -> unnecessary corners are appearing on item details screen
B017 | Closed | Closed | Humza | reel ordering -> numbers on cart icon are not appearing properly

## iOS
Bug ID | Status | ClickUp Status | Assigned To | Description | Expected Result | Actual Result | Assigned Date
B001 | Closed | Closed | Humza | Open the menu -> add products into cart -> give bottom margin to view cart button | The 'View cart' button should have a proper bottom margin. | The 'View cart' button lacks sufficient bottom margin | 2024-10-15
B002 | Closed | Closed | Humza | Cart -> minus icon UI issue | The minus (decrease quantity) icon should be clearly visible | The minus icon is not clearly visible | 2024-10-15
B004 | Closed | Closed | Humza | rating pop up -> text is hidig under the keyboard
B005 | Closed | Closed | Humza | rating pop up -> keyboard should get closed when user click anywhere on the page
B006 | Closed | Closed | Humza | contact us -> write msg -> not able to close the kayboard

## Coupon
Bug ID | Status | ClickUp Status | Assigned To | Description | Expected Result | Actual Result | Assigned Date
B001 | Closed | Closed | Sameed | deactivated coupons on portal are also visible on app (both on menu and cart page) | Deactivated coupons should not appear on the app | Deactivated coupons are also appearing | 2024-11-01
B002 | Closed | Closed | Sameed | Percentage ad fixed amount coupons: A coupon with a usage limit of 1 is still applying discounts on multiple uses. The system shows an "already availed" message on the second use but continues to reduce the order total on the order status screen. | The coupon should only apply once, with no further discounts on additional uses | The discount is still applied despite the "already availed" prompt, reducing the order total. | 2024-11-07

## Food App Promotions(Backend)
Bug ID | Status | ClickUp Status | Assigned To | Description | Expected Result | Actual Result | Assigned Date
B001 | Closed | Closed | Sameed | super admin: new record -> if offer type is free delivery then only delivery option should be selectable in offer type | When the offer type is set to "Free Delivery," the only selectable option in the offer type should be "Delivery | Currently, other options might be selectable, causing inconsistency | 2024-10-23
B003 | Closed | Closed | Sameed | super admin: new record -> add a field of 'No Of Redemption For Max Use' | A new field, "No Of Redemption For Max Use," should be added to allow super admins to set the maximum number of redemptions for a promotion | This field is currently missing | 2024-10-23
B004 | Closed | Closed | Sameed | super admin: new record -> make profile img field mandatory | The profile image field should be mandatory when creating a new record. | The profile image field is not mandatory | 2024-10-23
B005 | Closed | Closed | Sameed | Inactive promotions of super amdin are also visible to the admin | Inactive promotions should not be visible to the admin | Inactive promotions are still visible to the admin | 2024-10-23
B006 | Closed | Closed | Sameed | admin -> available promotions, requests, invites, active should be clickable so admin can see the complete details of that promotion | The promotions under "Available," "Requests," "Invites," and "Active" should be clickable to view full promotion details | These categories may not be clickable, preventing the admin from accessing detailed information. | 2024-10-23
B007 | Closed | Closed | Sameed | if any promotion is already in requests, invite or active then it should not be visible in available promotions list | admin: Promotions that are already in the "Requests," "Invites," or "Active" status should be excluded from the "Available Promotions" list | These promotions still appearing in the available list | 2024-10-23
B008 | Closed | Closed | Sameed | if super admin/admin sent request -> rejected with reason -> other party should get notification of rejection with the reason provided | If a request is rejected, the other party should receive a notification with the provided reason for rejection | Currently, notifications may not be sent, and the reason for rejection is also missing. | 2024-10-23
B009 | Closed | Closed | Sameed | if admin request for any promotion to super admin, super admin should get notification for that request (suggestion) | Super Admin should receive a notification when an admin sends a promotion request. | This notification might not be triggered, making the Super Admin unaware of incoming requests. | 2024-10-23
B012 | Closed | Closed | Sameed | admin: sent request to join -> show the correct prompt for request | When an admin sends a request to join, the correct prompt should be shown to confirm the request | The prompt is incorrect, leading to confusion about whether the request was successfully sent or assigned | 2024-10-23
B014 | Closed | Closed | Sameed | super admin: if any promotion is expired, make it deactivate or expired but don't show it as active | super admin: Expired promotions should automatically change status to "Deactivated" or "Expired" and not appear as active | Expired promotions are still shown as active, causing confusion about their availability. | 2024-10-23
B015 | Closed | Closed | Sameed | make discount amount field mandatory | Both the "Order type" and "Discount amount" fields should be mandatory when creating promotions | These fields are not be mandatory | 2024-10-23
B016 | Closed | Closed | Sameed | GIFs are not playing | GIFs should automatically play or animate as soon as they are loaded or interacted with | GIFs are not playing, remaining static | 2024-10-23
B017 | Closed | Closed | Sameed | admin: invites and requests promtions having pending status are also appearing on food app | pending promotions should not be visible on app until they are approved | Promotions with "Pending" status are also visible on the food app | 2024-10-24
B018 | Closed | Closed | Sameed | super admin deactivated restaurant from any promotion -> but on app that restaurant is still appearing on that promotion | Once a restaurant is deactivated from a promotion by the super admin, that restaurant should no longer appear as part of the promotion on the app | The deactivated restaurant is still appearing as part of the promotion on the food app. | 2024-10-24
B019 | Closed | Closed | Sameed | super admin request restaurant -> admin rejected promotion -> in app that restaurant is still apparing in the promotion | If the admin rejects the promotion requested by the super admin, the promotion should not be visible to on app | Despite being rejected by the admin, the promotion is still visible on the food app. | 2024-10-24
B020 | Closed | Closed | Sameed | restaurant accepted request of promotion but that in app that restaurant is missing | When a restaurant accepts the promotion request, it should appear in the food app as part of the promotion. | The restaurant is missing from the app, even after accepting the promotion request. | 2024-10-24
B021 | Closed | Closed | Sameed | order type is delivery but promotional discounts are also applying on pickup orders | Promotional discounts should only be applied to the order type defined on the portal | Promotional discounts are of delivery but incorrectly applied to pickup orders as well. | 2024-10-24
B022 | Closed | Closed | Sameed | edit -> add max amount and save -> amount not updating | After entering a new max amount and save the updated amount should be reflected immediately in the details. | The max amount is not updating after saving | 2024-10-25
B023 | Closed | Closed | Sameed | added a discount of 30% but its subtracting 30 AED | Entering a 30% discount should calculate a 30% reduction in the total price, not a fixed 30 AED deduction | Instead of calculating a percentage, the discount function is incorrectly applying a fixed amount | 2024-10-25
B025 | Closed | Closed | Sameed | create new promotion -> select price based listing in offering type -> add the max limit and save -> edit the same promotion -> price is missing | The Max Item Price Limit value should be saved and displaycorrectly upon re-editing | The Max Item Price Limit value does not save. | 2024-10-25
B026 | Closed | Closed | Sameed | price based lisiting: max limit is 25 but on app items priced above 25 are also appearing in the menu | Only items priced at 25 or below should appear in the item list | Items priced above 25 are also appearing in the menu list | 2024-10-26
B027 | Open | Open | Sameed | super admin fields and admin fields should be same for all promotions
B022 | Closed | Closed | Sameed | max limit is 25 but on app ttems priced above 25 are also appearing in the menu | Only items priced at 25 or below should be displayed in the menu | Items priced above 25 are also appearing in the menu | 2024-10-29
B023 | Closed | Closed | Sameed | featured restaurants are not appearing even when user is in the radius of the location | When the user is within the radius, featured restaurants should be displayed in the list. | No featured restaurants appear in the list, even when the user is in the correct radius. | 2024-10-31