## UAT Introduction & Scope
USER ACCEPTANCE TESTING (UAT) DOCUMENT FOR FOUGITO POS SYSTEM
Table of Contents A. Introduction B. Scope C. UAT Points
A. Introduction The User Acceptance Testing (UAT) document delineates the procedures and criteria for verifying the functionality and usability of the Point of Sale (POS) system. Its purpose is to ensure that the system adheres to specified requirements and is prepared for deployment.
B. Scope The UAT will concentrate on testing various features and functionalities of the POS system, including but not limited to:
1 | Dine-In Order: | Done
2 | Add New Items: | Done
3 | Increasing and Decreasing Item Quantity: | Done
4 | Cancellation of Item: | Done
5 | Table Switching: | Done
6 | Merge Table: | Done
7 | K-Slip: | Done
8 | K-Last: | Done
9 | E-Bill: | Done
10 | Date and Time on KOT: | Done
11 | Check Invoice: | Done
12 | Payment Methods: | Done
13 | Invoice Sharing: | Done
14 | Pickup Order: | Done
15 | Quick Order: | Done
16 | Increasing And Decreasing Items Quantity (Pickup): | Done
17 | Delivery Order: | Done
18 | Add New Items In Delivery Order: | Done
19 | Increasing And Decreasing Items Quantity (Delivery): | Done
20 | Switching From Dine-In to Pickup: | Done
21 | Favorite Menu Items: | Done
22 | Side Menu: | Done
23 | Printing Options: | Done
24 | Guest and Bill Report: | Done
25 | Category & Product Sales Report: | Done
26 | Delivery Staff Cash: | Done
27 | Share Invoice: | Done
28 | Rider Petty Cash: | Done
29 | Manage Order: | Done
30 | Bill Amendment: | Done
31 | Order Release: | Done
32 | Credit Order: | Done
33 | Purchase Order: | Done
34 | Meal Plan:
35 | Cash Drawer Closing: | Done
36 | Table Reservation: | Done
37 | Settings: | Done
38 | Menu Data Sync: | Done
39 | Menu Management: | Done
40 | Restaurant Is Open: | Done
41 | Check Printer: | Done
42 | Theme Settings: | Done
43 | Online Order Received on POS (Delivery) | Done
44 | Online Order Received on POS (Pickup) | Done
UAT Sign-off: Upon successful completion of all test cases and meeting the defined criteria, the UAT will be signed off by the designated stakeholders indicating acceptance of the Online Order Management feature on the POS system.

## UAT_Points
Activity Name | Pass | Fail | Remarks
1. Dine-In Order: | Press Shift + P for "P" & Shift+O for "O"
Create a New Order: Ensure the system allows initiating a new order. | P
Select Dine-In Option: Verify the ability to choose the dine-in option. | P
Assign a New Table: Check if tables can be assigned to orders. | P
View All Categories and Menu Items: Confirm visibility of all menu categories and items. | P
Add Selected Items to the Order: Ensure selected items are successfully added to the order. | P
Apply Percentage-Based Item Discounts: Verify the application of percentage-based discounts to items. | P
Write Special Instructions: Ensure the capability to add special instructions to items. | P
Adjust Item Quantities: Verify the ability to increase or decrease item quantities. | P
Add Items to the Cart: Ensure items are added to the cart for checkout. | P
Proceed to Checkout: Verify the checkout process for orders. | P
Apply Coupons: Confirm the application of coupons to orders. | P
Apply Percentage or Amount-Based Discounts: Verify the application of both percentage and amount-based discounts. | P
Assign Waiter Staff: Check if waiter staff can be assigned to orders. | P
Specify the Number of Guests: Confirm the ability to specify the number of guests for the order. | P
Include Additional Comments: Ensure the option to include additional comments for the order. | P
Check or Uncheck Print Kitchen Slip: Verify the option to print the kitchen slip. | P
Proceed to Checkout: Verify the checkout process for orders. | P
2. Add New Items:
Navigate to Dine-In Order: Verify navigation to the dine-in order section. | P
Use the Refresh Button: Ensure the functionality of the refresh button. | P
Select the Required Table: Confirm the selection of the table for adding new items. | P
Add New Items to the Order: Verify successful addition of new items to the order. | P
Proceed to Checkout: Ensure smooth transition to the checkout process. | P
Update the Order: Confirm that the order updates reflect the added items. | P
3. Increasing and Decreasing Item Quantity:
Access Dine-In Order: Verify access to the dine-in order section. | P
Utilize the Refresh Button: Ensure the functionality of the refresh button. | P
Choose the Required Table: Confirm selection of the table. | P
Proceed to Checkout: Ensure smooth transition to the checkout process. | P
Adjust Item Quantities using the (+) and (-) Buttons: Verify the functionality of adjusting item quantities. | P
Update the Order: Confirm that the order updates reflect the adjusted quantities. | P
4. Cancellation of Item:
Access Dine-In Order: Verify access to the dine-in order section. | P
Select the Required Table: Confirm selection of the table. | P
Proceed to Checkout: Ensure smooth transition to the checkout process. | P
Remove Items by Clicking on the (-) Button: Verify the ability to remove items from the order. | P
Update the Order: Confirm that the order updates reflect the removed items. | P
5. Table Switching:
Access Dine-In Order: Verify access to the dine-in order section. | P
Select the Desired Table: Confirm selection of the desired table. | P
Navigate to a New Table: Ensure smooth navigation to the new table. | P
Proceed to Checkout: Ensure smooth transition to the checkout process. | P
Update the Order: Confirm that the order updates reflect the switched table. | P
6. Merge Table:
Access Dine-In Order: Verify access to the dine-in order section. | P
Select the Required Table: Confirm selection of the table to merge. | P
Navigate to Another Table: Ensure smooth navigation to another table. | P
Choose the Desired Table to Merge: Confirm selection of the table to merge. | P
Combine the Tables: Verify successful merging of the tables. | P
7. K-Slip:
Print Kitchen Slip: Verify the functionality to print the kitchen slip. | P
8. K-Last:
Print the Last Kitchen Slip: Confirm the ability to print the last kitchen slip. | P
9. E-Bill:
Print Table Bill (E-Bill): Verify the functionality to print the table bill electronically. | P
10. Date and Time on KOT:
Check the Date and Time on the Kitchen Slip: Confirm that the date and time on the kitchen slip are accurate. | P
11. Check Invoice:
Calculation of Invoice: Verify the accuracy of invoice calculations. | P
Overall Discount: Confirm the application of overall discounts. | P
Discount Amount: Verify the correct calculation of discount amounts. | P
VAT Amount: Ensure the accurate calculation of VAT. | P
Date and Time: Confirm that date and time on the invoice are correct. | P
12. Payment Methods:
Cash: Test the payment process using cash. | P
Card: Test the payment process using a card. | P
Partial: Verify the functionality of partial payments. | P
Aggregator: Test payments made through aggregators. | P
Credit: Test credit payments. | P
Payment from QR Code: Verify payment process using QR code. | P
Share via WhatsApp Order Payment Link: Test payment sharing via WhatsApp. | P
Proceed Payment: Confirm successful completion of the payment process. | P
13. Invoice Sharing:
Share via WhatsApp: Test sharing invoice via WhatsApp. | P
Share via Email: Test sharing invoice via email. | P
Share via QR Code: Test sharing invoice via QR code. | P
14. Pickup Order:
Create a New Order: Ensure the ability to create a new pickup order. | P
Select Pickup: Verify selection of the pickup option. | P
Category (View All): Confirm visibility of all categories. | P
Menu (View All): Ensure visibility of all menu items. | P
Select Items (Add Items): Verify the ability to select and add items to the order. | P
Apply Item-Wise Discount by Percentage: Confirm the application of item-wise discounts by percentage. | P
Write Special Instructions: Ensure the capability to write special instructions for items. | P
Increase or Decrease Item Quantity: Verify the functionality to adjust item quantities. | P
Add to Cart: Ensure successful addition of items to the cart. | P
Checkout: Verify the checkout process. | P
Coupons: Confirm the application of coupons. | P
Discount (Percentage/Amount): Verify the application of both percentage and amount-based discounts. | P
Additional Comment: Ensure the option to include additional comments. | P
Print Kitchen Slip (Check/Uncheck): Verify the option to print the kitchen slip. | P
Place Order: Confirm successful placement of the order. | P
15. Quick Order:
Add New Items to Pickup Order: Verify the addition of new items to a pickup order. | P
Go to Pickup Order: Ensure smooth navigation to the pickup order section. | P
Refresh Button: Test the functionality of the refresh button. | P
Select the Required Order: Confirm selection of the required order. | P
Add Items: Ensure successful addition of items to the order. | P
Checkout: Verify the checkout process. | P
Update Order: Confirm that the order updates reflect the added items. | P
16. Increasing And Decreasing Items Quantity (Pickup):
Go to Pickup Order: Ensure access to the pickup order section. | P
Refresh Button: Test the functionality of the refresh button. | P
Select the Required Order: Confirm selection of the required order. | P
Checkout: Verify the checkout process. | P
Click on (-) (+) to Increase or Decrease: Verify the functionality to adjust item quantities. | P
Update Order: Confirm that the order updates reflect the adjusted quantities. | P
17. Delivery Order:
Create a New Order: Ensure the ability to create a new delivery order. | P
Add New Customer or Select an Existing Customer: Verify the option to add a new customer or select an existing one. | P
Verify Mobile Number: Confirm the validation of the mobile number. | P
Customer Name: Ensure accurate recording of customer name. | P
Delivery Information: Verify the options for delivery locations (Home, Office, Other). | P
Pin on Map: Ensure accurate pinning of the delivery location on the map. | P
Building & Street, Flat Number & Flat: Confirm accurate recording of address details. | P
Notes to Rider: Ensure the capability to add special instructions for the delivery. | P
Proceed: Confirm transition to order customization. | P
Category (View All): Ensure visibility of all menu categories. | P
Menu (View All): Confirm visibility of all menu items. | P
Select Items (Add Items): Verify the ability to select and add items to the order. | P
Apply Item-Wise Discount by Percentage: Confirm the application of item-wise discounts by percentage. | P
Write Special Instructions: Ensure the capability to write special instructions for items. | P
Increase or Decrease Item Quantity: Verify the functionality to adjust item quantities. | P
Add to Cart: Ensure successful addition of items to the cart. | P
Checkout: Verify the checkout process. | P
Coupons: Confirm the application of coupons. | P
Discount (Percentage/Amount): Verify the application of both percentage and amount-based discounts. | P
Select Delivery Staff: Confirm selection of delivery staff. | P
Petty Cash: Verify handling of petty cash for delivery orders. | P
Additional Comment: Ensure the option to include additional comments. | P
View Info (Customer Information): Confirm access to customer information. | P
Print Kitchen Slip (Check/Uncheck): Verify the option to print the kitchen slip. | P
Place Order: Confirm successful placement of the order. | P
18. Add New Items In Delivery Order:
Go to Delivery Order: Ensure access to the delivery order section. | P
Refresh Button: Test the functionality of the refresh button. | P
Select the Required Order: Confirm selection of the required order. | P
Add Items: Ensure successful addition of items to the order. | P
Checkout: Verify the checkout process. | P
Update Order: Confirm that the order updates reflect the added items. | P
19. Increasing And Decreasing Items Quantity (Delivery):
Go to Delivery Order: Ensure access to the delivery order section. | P
Refresh Button: Test the functionality of the refresh button. | P
Select the Required Order: Confirm selection of the required order. | P
Checkout: Verify the checkout process. | P
Click on (-) (+) to Increase or Decrease: Verify the functionality to adjust item quantities. | P
Update Order: Confirm that the order updates reflect the adjusted quantities. | P
20. Switching From Dine-In to Pickup:
Go to Dine-In Order: Ensure access to the dine-in order section. | P
Select the Required Table: Confirm selection of the required table. | P
Click on Pickup: Verify the transition from dine-in to pickup. | P
Checkout: Ensure smooth transition to the checkout process. | P
Update Order: Confirm that the order updates reflect the switch to pickup. | P
21. Favorite Menu Items:
Test the functionality of adding and accessing favorite menu items. | P
22. Side Menu:
Test the functionality and accessibility of the side menu. | P
23. Printing Options:
Test various printing options including last slip, duplicate slip, and pending payments. | P
24. Guest and Bill Report:
Verify the accuracy and accessibility of guest and bill reports. | P
25. Category & Product Sales Report:
Verify the accuracy and accessibility of category and product sales reports. |  | O | Total Sale without Tax, Gross Sale With Tax and delivery charges are wrong.
26. Delivery Staff Cash:
Test the functionality related to handling cash for delivery staff. | P
27. Share Invoice:
Test the options for sharing invoices via WhatsApp, email, and QR code. | P
28. Rider Petty Cash:
Test the functionality related to handling petty cash for riders. | P
29. Manage Order:
Test the functionality related to managing orders, including cancellation, amendment, release, and credit. | P
30. Bill Amendment:
Test the functionality related to amending bills. | P
31. Order Release:
Test the functionality related to releasing orders. | P
32. Credit Order:
Test the functionality related to processing credit orders. | P
33. Purchase Order:
Test the functionality related to processing purchase orders. | P
34. Meal Plan:
Test the functionality related to meal planning.
35. Cash Drawer Closing:
Test the functionality related to closing cash drawers. | P
36. Table Reservation:
Test the functionality related to table reservations. | P
37. Settings:
Test the functionality related to POS settings. | P
38. Menu Data Sync:
Test the functionality related to syncing menu data. | P
39. Menu Management:
Test the functionality related to managing menus. | P
40. Restaurant Is Open:
Test the functionality related to indicating restaurant status. | P
41. Check Printer:
Test the functionality related to checking printers. | P
42. Theme Settings:
Test the functionality related to setting theme. | P
43. Online Order Received on POS (Delivery)
Receive Online Order Notification: Receive notification of an online order. | P
Close Notification: Dismiss the notification. | P
Navigate to Online Order Section: Access the online order management section on the POS. | P
Go to Delivery Order: Ensure access to the delivery order section. | P
Select Order for Delivery: Choose the specific order intended for delivery. | P
Verify Order Information: Confirm details such as items, quantities, and delivery address. | P
Verify Amount Calculation: Ensure the accuracy of the total amount calculated. | P
Change Order Status to Confirmed: Mark the order as confirmed for processing. | P
Update Order Status to Ready: Change the status to Ready. | P
Update Order Status to Assigned to Delivery Boy: Assign the order to the delivery personnel. | P
Verify Petty Cash Management Functionality: Ensure proper recording of cash transactions, if applicable. | P
44. Online Order Received on POS (Pickup)
Receive Online Order Notification: Receive notification of an online order. | P
Close Notification: Dismiss the notification. | P
Navigate to Online Order Section: Access the online order management section on the POS. | P
Go to Pickup Order: Ensure access to the pickup order section. | P
Select Order for Pickup: Choose the specific order intended for pickup. | P
Verify Order Information: Review items and quantities. | P
Verify Amount Calculation: Ensure the accuracy of the total amount calculated. | P
Change Order Status to Confirmed: Confirm the order for pickup. | P
Update Order Status to Ready: Change the status to Ready. | P
Proceed with Payment: Complete the payment process for the order. | P
UAT document ends here. | Date:
Sign Off: